## TASKS
TASK | RESOURCE | BACK UP RESOURCE
PM | Carol | Joan
PULL DATA | Kashifa | Carol
CLEAN DATA | Kashifa | Carol
COMBINE DATA (for Storage) | Joan | Carol
COMBINE DATA (for ML) | Venkata | Carol
DEFINE THE SCHEMA | Carol | Joan
BUILD THE SCHEMA | Carol | Joan
IMPORT THE DATA | Joan | Carol
DEFINE THE QUESTIONS | Mohammed | Carol
CREATE VISUALIZATIONS | Joan | Venkata
WEB PAGE | Joan | Carol
MACHINE LEARNING | Venkata | Kashifa
FLASK ROUTES | Carol | Venkata
GIT REPOSITORY | Carol | Kashifa
Zoom - | Carol | Joan
PRESENTATION | Carol | Team

## PM
TASK | RESOURCE | BACK UP RESOURCE
PM | Carol | Joan
1 | Create Project Guidelines and share
2 | Track and document all data used
3 | Create a task document and timeline
4
5
6
7

## PULL DATA
PULL DATA | Kashifa | Carol
1 | Identify sources
2 | document sources with required citations of sources used.
3 | save any documentation about the source and place on Git repository with data
4 | Retrieve data about the following:
Infant mortality for the US.
Infant mortality for Ohio.
5 | Include the following VIEWS whenever possible:
YEAR
STATE
COUNTY
Rates/ Birth rates versus Death rates
6 | Additionally, find data regarding
Race of the Mom
Gender of the baby
Date of death
Mother's education level
Mother's age
Mother's number of prenatal visits
Urban versus rural data
Any geo-spacial data about death or mom
Mom's poverty level or median income levels
poverty levels or income levels of the county / state or region
7 | Import Data into a Pandas notebook
8 | Include the location of the data on GIT into the notebook
9 | Include the link to where the data was gathered on the notebook
10 | Make notation of what variables were used to gather the data
11 | Place the data in the repository under DATA and whichever folders makes the most sense to what was gathered.

## CLEAN DATA
CLEAN DATA | Kashifa | Carol
1 | pull the data into a pandas note book or similar for cleaning OR use notebook from PULLING data step
2 | Be sure to DOCUMENT any dropped values
3 | Be sure to KEEP a copy of the data as it was pulled
4 | Clean the data so that the headers are clear to what we are reviewing
5

## COMBINE DATA (for Storage)
COMBINE DATA (for Storage) | Joan | Carol
1 | Identify all the data needing storage for the WEBSITE and Visualizations
2 | Create joins on all the data needed to go into each table
3 | Combine the data into each unique table
4 | Validate the data does not contain duplications or unexpected nulls as a result
5 | Document the combinations for reference
6 | Coordinate the input of data into the data base
7 | Communicate tables and data needed so that the schema can be defined and built

## COMBINE DATA (for ML)
COMBINE DATA (for ML) | Venkata | Carol
1 | Identify all the data needing storage for the Machine learning tasks
2 | Create joins on all the data needed to go into each table
3 | Combine the data into each unique table
4 | Validate the data does not contain duplications or unexpected nulls as a result
5 | Document the combinations for reference
6 | Coordinate the input of data into the data base
7 | Communicate tables and data needed so that the schema can be defined and built

## BUILD THE SCHEMA
DEFINE THE SCHEMA | Carol | Joan
1 | Create a DRAFT ERD for use as the data is being gathered
2 | Once all data is gathered, cleaned, combined and ready
Build the final ERD based on the end needs of the data
3 | Document the ERD formally and communicate to the team

## IMPORT THE DATA
IMPORT THE DATA | Joan | Carol
1 | Once all the schema is build and the database is ready, begin to import all the data
2 | once all the data is imported, validate all the data
3 | Identify any data that needs to be imported via API or on the fly
4 | Document and communicate to the team, once the data base is complete with data

## DEFINE THE QUESTIONS
DEFINE THE QUESTIONS | Mohammed | Carol
1 | after consultation with the team, keep documenting and narrowing down the set of questions that the machine learning and visualizations will ask
2 | Keep good documentation on any changes in the focus of the story
3 | Be sure to document the final questions, and review all the story and data to be sure we answered the questions

## CREATE VISUALIZATIONS
CREATE VISUALIZATIONS | Joan | Venkata
1 | Begin to review all the data available and decide what we can reflect in visualizations
2 | Once the data is cleaned, start the process of creating visualizations
3 | document the names, technologies, and context of all the visualizations
4 | Share the locations and access of the visualizations to all the team members
5 | Define how we will access these visualizations in the web site
6

## WEB PAGE
WEB PAGE | Joan | Carol
1 | Draw / create a draft version
2 | Create the basic HTML
3 | Create the basic CSS
4 | Test the basic HTML and CSS
5 | As the project progresses, build what is needed to support the vision and story we want to tell
6 | Document everything within <!comments> and in the project documents, links etc… and final credits

## MACHINE LEARNING
MACHINE LEARNING | Venkata | Kashifa
1 | Define the Machine learning we can accomplish with the data that we have
2 | Define the data needed and how the data will be imported into the models
3 | Define how the web site will work with the machine learning
4 | Work with the web site development to coordinate output
5 | Work with the database development to coordinate input
6 | work with the data cleaning and prepping to coorindate data needed
7 | Build and test the model needed
8 | Train the model
9 | Communicate results of the model testing and training
10 | Save all successful models

## FLASK ROUTES
FLASK ROUTES | Carol | Venkata
1 | develop the app.py
2 | Coordinate with the data, database, visualization, website and machine learning teams to define what routes will be needed
3 | Build needed routes
4 | Test needed routes
5 | Document and communicate all routes built and the testing results

## GIT Repository
GIT REPOSITORY | Carol | Kashifa
| 1 | Build the repository
| 2 | maintain all the folders in the master
| 3 | Keep all the data within clean and orderly and well documented
| 4 | keep the Wiki and Read.me up to date
5